## Detailed_Sizing (hidden)
Candidate List | Tasks | Person Days | Comments
#1 Alert notification executable options | 50
| Schema | 5
| Scoping/Design Document (Usage Doc) | 15
| XML Snippet (Add/Edit/Delete/Enable/Disable) | 5
| Backend handling | 6
| Build changes | 1
| Unit Testing | 2
| Integration Testing | 2
| QA (TC development/Review/Execution) | 12
| Doc | 2
#2 Alert definition (Edit Rule) | 14
| Scoping Doc | 3
| GUI | 4
| Unit Testing | 1
| QA (TC development/Review/Execution) | 5
| Doc | 1
#3 Alert definition (Alert Policy) | 15
| Scoping Doc | 3
| GUI | 6
| Unit Testing | 1
| QA (TC development/Review/Execution) | 4
| Doc | 1
#4 Alert supporting evidence (Subject Line) | 8.5
| Scoping Doc | 2
| Scoping Doc | 3
| QA (TC development/Review/Execution) | 3
| Doc | 0.5
#5 RFE: Maintain the Event Timestamp from PULLED event sources | 90
| Scoping Doc | 10
| Design Doc | 25
| Backend | 25
| Unit Testing | 5
| QA (TC development/Review/Execution) | 25 | All Criteria alerts
| Doc | 0
#6 RFE: Ability to alert on ThreatVue Control Status | 89
(ThreatVue: Alerts, Reports, Forensics) | Scoping Doc | 10
| Design Doc | 15
| GUI | 12 | Alert=3d, Report=5d, Forensics=1d
| Backend | 18 | ELF Construction i.e Delta & Monitoring=3d, Parsing&Reporting=6d, Forensics=3d, Alert=3d
| GUI Unit Testing | 3
| Backend Unit Testing | 6
| Integration Testing | 3
| QA (TC development/Review/Execution) | 20 | Alerts, Forensics Reports - Including Workbench & Drilldowns,
| Doc | 2
#7 Administrative control/sub-control | 26
(12.1 - No unauthorized administrator accounts) | Scoping Doc | 3
| GUI | 4 | Whitelist
| Backend & Unit Testing | 6
| GUI Unit Testing | 1
| Integration Testing | 1
| QA (TC development/Review/Execution) | 10
| Doc | 1
#8 Administrative control/sub-control | 19
(12.3 - Require changing passwords) | Scoping Doc | 3
| Backend | 5
| Unit Testing | 2
| QA (TC development/Review/Execution) | 8
| Doc | 1
#9 Administrative control/sub-control | 19
(12.5 - Require complex passwords) | Scoping Doc | 3
| Backend | 5
| Unit Testing | 2
| QA (TC development/Review/Execution) | 8
| Doc | 1
#10 Administrative control/sub-control | 19
(12.9 - Restrict password reuse) | Scoping Doc | 3
| Backend | 5
| Unit Testing | 2
| QA (TC development/Review/Execution) | 8
| Doc | 1
#11 Refresh OpenSSL | 18
| Scoping Doc | 2
| Backend | 7
| Unit Testing | 2
| QA (TC development/Review/Execution) | 7
| Doc | 0
#12 Ability to limit concurrent sessions of same username | 23
| Scoping Doc | 4
| GUI | 4
| Backend & Unit Testing | 6
| Unit Testing | 2
| Integration Testing | 1
| QA (TC development/Review/Execution) | 5
| Doc | 1
#13 Link the entire threat path | 10
| Scoping Doc | 3
| GUI | 2
| Unit Testing | 1
| QA (TC development/Review/Execution) | 3
| Doc | 1
#14 Feature driven configuration | 1200 | 1200
Scoping Doc
Backend
Unit Testing
QA (TC development/Review/Execution)
Doc
#15 Merge NGS v3.0 features in SecureVue | 207
| Scoping Doc | 10
| Design Doc | 15 | License Upgrade
| Installer Changes | 19 | Mode of Installation, Local DC
| Backend Licensing Changes | 24 | Unified Licensing=10d, License Upgrade=10d
| GUI Licensing Changes | 7
| Unit Testing (GUI) | 2
| Unit Testing (Backend) | 2
| Integration Testing | 2
| Backend Threat Vue | 8 | Build Changes, DC Collection, Mainengine Changes
| GUI Threat Vue | 7
| Unit Testing (GUI) | 2
| Unit Testing (Backend) | 2
| Integration Testing | 2
| Backend Node Management | 15 | Node management with Manage/unmanaged licensing concept, licensing includes single nodetype license., Bulk Licensing Changes, Same node to multiple network DC's, Bulk Nodes handling
| GUI Node Management | 8
| Unit Testing (GUI) | 1
| Unit Testing (Backend) | 1
| Integration Testing | 1
| Backend Nmap Discovery | 3
| GUI Nmap Discovery | 3
| Unit Testing (GUI) | 1
| Unit Testing (Backend) | 1
| Integration Testing | 1
| Backend Activation & Unit Testing | 2
| GUI Activation & Unit Testing | 2
| Integration Testing | 1
| QA (TC development/Review/Execution) | 55 | License=15d (Includes combinations), Installer=5d, NodeManagement=15d, Nmap=6d, Activation=3d, TDB=5d
| Doc | 10
#16 Remove tree at flow reports | 11 |  | We should obtain this capability as part of merge of USA and NGS code base
| Scoping Doc | 3
| Backend | 3
| Unit Testing | 1
| QA (TC development/Review/Execution) | 4
| Doc | 0
#17 RFE: Ability to Report on ThreatVue |  |  | This will be covered as part of ID#6
#18 Better status on ThreatVue evaluation | 22
| Scoping Doc | 5
Design Doc
| Backend & Unit Testing | 4
| GUI | 4
| GUI Unit Testing | 1
| Integration Testing | 1
| QA (TC development/Review/Execution) | 6
| Doc | 1
#19 Improved list configuration | 24
| Scoping Doc | 4
| Design Doc | 6
| GUI | 7
| Unit Testing | 1
| QA (TC development/Review/Execution) | 5
| Doc | 1
#20 Option to include full details in PDF/HTML export | 35.5
| Scoping Doc | 5
| Design Doc | 8
| Backend | 15
| Unit Testing | 1
| QA (TC development/Review/Execution) | 6
| Doc | 0.5
#21 Alert group (& RBAC) | 18 |  | Will provide default policies as Importable format instead of providing by default
| Scoping Doc | 4
| Categorizing Alerts | 7
| Unit Testing | 1
| QA (TC development/Review/Execution) | 5
| Doc | 1
#22 Alert group (& RBAC) |  |  | Excluded
#23 Alert supporting evidence (Notification Body) | 47.5
| Scoping Doc | 5
| Design Doc | 12
| GUI | 8
| Backend | 12
| GUI Unit Testing | 1
| Backend Unit Testing | 1
| Integration Testing | 1
| QA (TC development/Review/Execution) | 7
| Doc | 0.5
Table of Contents for Alerts | 44.5
| Scoping Doc | 5
| Design Doc | 12
| GUI | 10
| Backend | 7
| GUI Unit Testing | 1
| Backend Unit Testing | 1
| Integration Testing | 1
| QA (TC development/Review/Execution) | 7
| Doc | 0.5
#24 Suppressing Alerts | 50
| Scoping Doc | 5
| Design Doc | 12
| GUI | 7
| Backend | 12
| GUI Unit Testing | 1
| Backend Unit Testing | 1
| Integration Testing | 1
| QA (TC development/Review/Execution) | 10
| Doc | 1
#25 Port/protocol sub-control (flows) | 28.5
| Scoping Doc | 4
| Design Doc | 8
| Backend | 8
| Backend Unit Testing | 1
| QA (TC development/Review/Execution) | 7
| Doc | 0.5
#26 Port/protocol sub-control (flrewall allow) | 28.5
| Scoping Doc | 4
| Design Doc | 8
| Backend | 8
| Backend Unit Testing | 1
| QA (TC development/Review/Execution) | 7
| Doc | 0.5
#27 SANS20 Control Mapping | 20
| Scoping Doc | 4
| GUI | 4
| Backend | 3 | To handle multiple third party standards
| GUI Unit Testing | 1
| Backend Unit Testing | 1
| Integration Testing | 1
| QA (TC development/Review/Execution) | 5
| Doc | 1
#28 Can't collect multiple file types from 1 system | 40
| Scoping Doc | 8
| Design Doc | 8
| GUI | 5
| Backend | 8
| GUI Unit Testing | 1
| Backend Unit Testing | 2
| Integration Testing | 1
| QA (TC development/Review/Execution) | 7
| Doc | 0
#29 Character limitation in User e-mail address | 12
| Scoping Doc | 4
| GUI & Unit Testing | 3
| Backend & Unit Testing | 3
| QA (TC development/Review/Execution) | 2
| Doc | 0
#30 Flexible scan options | 26
| Scoping Doc | 5
| GUI & Unit Testing | 6
| Backend & Unit Testing | 6
| Integration Testing | 1
| QA (TC development/Review/Execution) | 7
| Doc | 1
#31 Simplified node management | 59
| Scoping Doc | 10
| Design Doc | 15
| GUI | 8
| Backend | 2
| GUI Unit Testing | 2
| Backend Unit Testing | 1
| Integration Testing | 1
| QA (TC development/Review/Execution) | 15
| Doc | 5
#32 Multi-line parsing | 0 |  | R & D (Can we push this to device support team)
#33 Feature Request for role Based Access |  |  | Excluded
#34 Granular control for Monitors tab with Role based access | 52
| Scoping Doc | 6
| Design Doc | 12
| GUI | 7
| Backend | 12
| GUI Unit Testing | 2
| Backend Unit Testing | 2
| Integration Testing | 1
| QA (TC development/Review/Execution) | 8
| Doc | 2
#35 Add ability to email reports not compressed | 0 |  | Will wait until Brian comments
#36 Introduce concept of "blacklist" | 36
| Scoping Doc | 6
| Design Doc | 6
| GUI | 8
| Backend | 5
| GUI Unit Testing | 1
| Backend Unit Testing | 1
| Integration Testing | 1
| QA (TC development/Review/Execution) | 6
| Doc | 2
#37 List import/export | 30
| Scoping Doc | 5
| Design Doc | 6
| GUI | 4
| Backend | 5
| GUI Unit Testing | 1
| Backend Unit Testing | 1
| Integration Testing | 1
| QA (TC development/Review/Execution) | 6
| Doc | 1
#38 Nmap scanning from Linux DC & Linux based DHCP collection | 16 |  | Note: Only Nmap is considered.
| Scoping Doc | 5
| Backend | 4
| Backend Unit Testing | 1
| QA (TC development/Review/Execution) | 6
| Doc | 0
#39 Remove license checks post collection (parsing, etc.,) | 32
| Scoping Doc | 10
| Backend | 11
| Backend Unit Testing | 3
| QA (TC development/Review/Execution) | 8
| Doc | 0
#40 Move Database collection from Mainengine to DC completely | 99
| Scoping Doc | 10
| Design Doc | 12
| GUI | 7
| Backend | 17
| GUI Unit Testing | 2
| Backend Unit Testing | 3
| Integration Testing | 1
| QA (TC development/Review/Execution) | 45
| Doc | 2
#41 Defects\enhancements in BZ pushed from 3.0 | 100
| Identification of bugs (Either to Fix/Close/Defer) | 20 | Including all NGS & SV bugs
| Bug Fix | 45 | Tentative estimates (Considered only for 125 bugs)
| QA (Bug Verification) | 30
| Doc | 5
#42 Evaluate SANS Gaps | 0
#43 Add Rapid7 to Control 1 & 4 | 19 |  | Rapid7 for Control 1 only
| Scoping Doc | 5
| Backend | 5
| Backend Unit Testing | 1
| GUI + Unit Testing | 2
| QA (TC development/Review/Execution) | 5
| Doc | 1
#44 Export to Word & CSV | 18.5 |  | For ThreatVue dashboard & Reporting
| Scoping Doc | 4
| GUI | 2
| Backend | 4
| GUI Unit Testing | 1
| Backend Unit Testing | 2
| Integration Testing | 1
| QA (TC development/Review/Execution) | 4
| Doc | 0.5
#45 Compliance Policy |  |  | This task covers under Configurability. Need to confirm on Upgrade support.
#46 Removal of DataProcessor GUI functionality | 18
| Scoping Doc | 5
| Installer | 3
| Unit Testing | 1
| QA (TC development/Review/Execution) | 7
| Doc | 2 | Need Confirmation
Upgrade Tasks: NGS 3.0 - SV 3.6.6 | 0 | 275
| Installer Changes |  | Service Names, Uninstall key
Parser Patterns
| Reports |  | Queries.xml, Sourcecols.xml, drillmap.xml, dbqueries.ext
Forensics
| Dashboard |  | Dashboards.xml
Encryption
| Folder Structure |  | Language dll issues, File name (SRMSyslog, NGSLicense…)
QA (TC development/Review/Execution)
Upgrade Tasks: SV 3.6.0/3.6.5 - SV 3.6.6 | 0 | 175
Licensing Upgrade
Add Bulk Licensed Nodes to Node Manager
Threat Controls
Node Ips across Multiple Networks
QA (TC development/Review/Execution)
Code Merges | 129
| SV3.6.6 Code Merges to Trunk | 80
| QA (TC development/Review/Execution) | 47
| Doc | 2
Code Merges | 10
| Q1H2 - Content Code Merges | 5
| QA (TC development/Review/Execution) | 5
| Doc | 0
Code Merges | 0
| NGS301 Code Merges | 0
| QA (TC development/Review/Execution) | 0
| Doc | 0
| 2824 | 3272
Note on A105: Author: Yet to fill complete details
Note on C382: Author: Tentative
Note on C392: Author: Tentative

## Summarized_Sizing (hidden)
ID | Priority | Theme | Feature Candidate | Detailed Scoping | T-shirt size | Confidence | Total Person Days | Dev | Testing | Doc
1 | P2 | Alerts | Alert notification executable options |  | XL | 80%
2 | P2 | Alerts | Alert definition |  | L | 100%
3 | P2 | Alerts | Alert definition |  | L | 100%
4 | P1 | Alerts | Alert supporting evidence (Subject Line) |  | L | 100% | 8.5 | 5 | 3 | 0.5
5 | P2 | Alerts | RFE: Maintain the Event Timestamp from PULLED event sources |  | XL | 10%
6 | P1 | Alerts ThreatVue | RFE: Ability to alert on ThreatVue Control Status | YES | XL | 100% | 89 | 67 | 20 | 2
7 | P1 | New Controls | Administrative control/sub-control |  | XL | 100% | 26 | 15 | 10 | 1 | [SV-SM] Design is already approved
8 | P1 | New Controls | Administrative control/sub-control |  | XL | 100% | 19 | 10 | 8 | 1 | [SV-SM] Design is already approved
9 | P1 | New Controls | Administrative control/sub-control |  | XL | 100% | 19 | 10 | 8 | 1 | [SV-SM] Design is already approved
10 | P1 | New Controls | Administrative control/sub-control |  | XL | 100% | 19 | 10 | 8 | 1 | [SV-SM] Design is already approved
11 | P1 | Core | Refresh OpenSSL |  | XL | 80% | 18 | 11 | 7 | 0
12 | P1 | Customization | Ability to limit concurrent sessions of same username | YES | XL | 100% | 23 | 17 | 5 | 1
13 | P1 | Customization | Link the entire threat path | YES | L | 100% | 10 | 6 | 3 | 1
14 | P1 | Pdt Configurability | Feature driven configuration | YES | XL |  | 1200
15 | P1 | NGS 3.0 Feature Merges | Merge NGS v3.0 features in SecureVue | YES | XL | 70% | 207 | 142 | 55 | 10 | Geoff - please rename this to NGS 3.0 Feature Merges (or something similar) [SV-SM] Done
19 | P1 | ThreatVue | Improved list configuration | YES | XL | 100% | 24 | 18 | 5 | 1
21 | P2 | Alerts | Alert group (& RBAC) |  | XL | 100%
23 | P2 | Alerts | Alert supporting evidence (Notification Body) |  | XL | 90%
| P1 | Alerts | Table of Contents for Alerts | YES | XL | 90% | 44.5 | 37 | 7 | 0.5
24 | P2 | Alerts | Suppressing Alerts |  | XL | 90%
25 | P1 | New Controls | Port/protocol sub-control (flows) | YES | XL | 80% | 28.5 | 21 | 7 | 0.5 | Geoff - make these P1's w/ 0 size & note will be included in 20% bucket for Controls [SV-SM] Considered
26 | P1 | New Controls | Port/protocol sub-control (flrewall allow) | YES | XL | 80% | 28.5 | 21 | 7 | 0.5 | Geoff - make these P1's w/ 0 size & note will be included in 20% bucket for Controls [SV-SM] Considered
27 | P1 | New Controls | SANS20 Control Mapping | YES | XL | 100% | 20 | 14 | 5 | 1 | Geoff - make these P1's w/ 0 size & note will be included in 20% bucket for Controls [SV-SM] Considered
28 | P2 | Core | Can't collect multiple file types from 1 system |  | XL | 70%
29 | P2 | Customization | Character limitation in User e-mail address |  | M | 100%
30 | P2 | NMAP | Flexible scan options |  | XL | 100%
31 | P2 | Simplified Node Mgmt | Simplified node management |  | XL | 90%
34 | P2 | RBAC | Granular control for Monitors tab with Role based access |  | XL | 90%
36 | P1 | ThreatVue | Introduce concept of "blacklist" | YES | XL | 100% | 36 | 28 | 6 | 2
37 | P1 | ThreatVue | List import/export | YES | XL | 100% | 30 | 23 | 6 | 1
38 | P2 | ThreatVue | Nmap scanning from Linux DC & Linux based DHCP collection |  | L | 90%
40 | P2 | Arch. Cleanup | Move Database collection from Mainengine to DC completely |  | XL | 70%
41 | P1 | Bugs Cleanup | Defects\enhancements in BZ pushed from 3.0 |  | XL | 80% | 100 | 65 | 30 | 5
42 | P1 | New Controls | Evaluate SANS Gaps | YES | XL |  | #REF! |  |  |  | Geoff - please rename this 'Additional Controls' [SV-SM] Done
43 | P1 | New Controls | Add Rapid7 to Control 1 & 4 |  | XL | 90% | 19 | 13 | 5 | 1
44 | P2 | ThreatVue | Export to Word & CSV |  | XL | 90%
46 | P1 | Core | Removal of DataProcessor GUI functionality | YES | L | 90% | 18 | 15 | 7 | 2
| P1 | Upgrade | Upgrade: NGS 3.0 - SV 3.6.6 | YES | XL | 70% | 275
| P1 | Upgrade | Upgrade: SV 3.6.0/3.6.5 - 3.6.6 | YES | XL | 80% | 175
| P1 | Code Merges | SV3.6.6 Code Merges to Trunk |  | XL | 90% | 129 | 82 | 47 | 0 | Geoff - why are code merges so expensive? We already have 200 days for merging NGS 3.0 stuff?? [SV-SM] These are the code merges of 3.6.5 till July end
| P1 | Code Merges | Q1H2 - Content Code Merges |  | L | 90% | 10 | 5 | 5 | 0
| P1 | Code Merges | NGS3.0.1 Code Merges |  | XL | 90% | 0 | 0 | 0 | 0 | Yet to fill
| P1 | Hardening | Scalability |  | XL | 80% | 40 | 0 | 40 | 0
| P1 | Hardening | Sanity and Regression |  | XL | 90% | 100 | 0 | 100 | 0
| P1 | Hardening | Final Regression |  | XL | 90% | 60 | 0 | 60 | 0
| P1 | Hardening | Beta Feedback & Bug fixes |  | XL | 80% | 165 | 110 | 50 | 5
[6 empty] | Total: | #REF! | 745 | 514 | 38
Excluded from estimation because of less clarity or merged with other item(s)
16 | P1 | Reports | Remove tree at flow reports |  | L | 100% | 11 | 7 | 4 | 0 | [SV-SM] Will be covered as part of Configurability
17 | P1 | Reports | RFE: Ability to Report on ThreatVue
18 | P1 | ThreatVue | Better status on ThreatVue evaluation | YES | XL | 80% | 22 | 15 | 6 | 1 | [SV-SM] To be covered in NGS 3.0.1
20 | P1 | ThreatVue | Option to include full details in PDF/HTML export | [7 empty] | Geoff - we need to get this in the first NGS CP … so should not be includede here [SV-SM] Moved to below Excluded table
22 | P2 | Alerts | Alert group (& RBAC)
32 | P1 | Parser | Multi-line parsing
33 | P2 | RBAC | Feature Request for role Based Access
35 | P2 | Reports | Add ability to email reports not compressed
39 | P1 | Arch. Cleanup | Remove license checks post collection (parsing, etc.,) |  | XL | 80% |  |  |  |  | [SV-SM 6/28] License check removal was being implemented as part of Product Configurability.
45 | P1 | Licensing | Compliance Policy
Note on F1: T-shirt size - (S) Small - 1 day or less (M) Medium - 1 day to 1 week (L) Large - 1 week to 3 weeks (XL) Ex-Large - 3+ weeks
Note on I1: Author: Scoping/Design & Implimentation
Note on J1: Author: TC Development/Execution
Note on H35: Author: 20% of Available Time
Note on D53: Author: This will be covered as part of ID#6

## Estimates_AfterScoping (hidden)
Task | Total | Scope | Design | Backend | GUI | QA | Doc
Alerts | 53
Alert supporting evidence (Subject Line) |  | 2 |  | 3 |  | 3 | 0.5
Table of Contents for Alerts |  | 5 | 12 | 8 | 12 | 7 | 0.5
Alerts ThreatVue | 62
RFE: Ability to alert on ThreatVue Control Status |  | 10 | 12 | 10 | 8 | 20 | 2
Arch. Cleanup
Bugs Cleanup (Defects\enhancements in BZ pushed from 3.0) | 60
Code Merges | 102
SV3.6.6 Code Merges to Trunk |  |  |  | 20 | 20 | 40 | 2
Q1H2 - Content Code Merges |  |  |  | 10 | 5 | 5 | 0
NGS3.0.1 Code Merges
Core | 43
Refresh OpenSSL |  | 8 | 9 | 0 | 8 | 0
Removal of DataProcessor GUI functionality |  | 5 |  | 4 | 0 | 7 | 2
Customization | 33
Ability to limit concurrent sessions of same username |  | 4 |  | 6 | 7 | 5 | 1
Link the entire threat path |  | 3 |  |  | 3 | 3 | 1
New Controls | 332
Administrative control/sub-control |  | 1.5 |  | 6 | 6 | 10 | 1
Administrative control/sub-control |  | 1.5 |  | 4 | 4 | 8 | 1
Administrative control/sub-control |  | 1.5 |  | 4 | 4 | 8 | 1
Administrative control/sub-control |  | 1.5 |  | 4 | 4 | 8 | 1
Add Rapid7 to Control 1 & 4 |  | 5 | 0 | 6 | 2 | 5 | 1
Port/protocol sub-control (flows) |  | 4 | 5 | 10 | 4 | 10 | 2
Port/protocol sub-control (flrewall allow) |  | 4 | 5 | 6 | 4 | 10 | 2
SANS20 Control Mapping |  | 4 |  | 4 | 6 | 5 | 1
Evaluate SANS Gaps |  | 45 |  | 34 | 18 | 43 | 7
NGS 3.0 Feature Merges | 231
Merge NGS v3.0 features in SecureVue |  | 15
Design: Merge NGS v3.0 features (Upgrade) - SV360/5 to SV366 (Bulk Nodes Handling) |  |  |  |  | 15 | 4
Design: Merge NGS v3.0 features (Upgrade) - SV360/5 to SV366 (License Upgrade) |  |  |  |  | 12 | 3
Merge NGS v3.0 features (Upgrade) - SV360/5 to SV366 (Bulk Nodes Handling) |  |  | 10 | 5 | 7 | 2
Merge NGS v3.0 features (Upgrade) - SV360/5 to SV366 (License Upgrade) |  |  | 5 | 0 | 7 | 0
Merge NGS v3.0 features: Installer Changes |  |  | 15 | 0 | 6 | 0
Merge NGS v3.0 features: ThreatVue Merges |  |  | 4 | 5 | 6 | 0
Merge NGS v3.0 features: Node Discovery |  |  | 4 | 6 | 7 | 0
Merge NGS v3.0 features: Node IPs across multiple DCs of same network |  |  | 3 | 3 | 6 | 0
Merge NGS v3.0 features: Miscellaneous Features |  |  | 1 | 1 | 3 | 0
Unified Node License |  |  | 8 | 10 | 10 | 0.5
Removal of Bulk license |  |  | 6 | 5 | 20 | 1
Activation |  |  | 1 | 2 | 2 | 0.5
Doc | [6 empty] | 10
NMAP
Pdt Configurability | 972.7
Feature driven configuration |  |  |  | 266.5 | 305.5 | 269 | 53.7
Config Genarator |  |  |  | 41 | 12 | 20 | 5
RBAC
Reports
Simplified Node Mgmt
Hardening | 365
Scalability | [5 empty] | 40
Sanity and Regression | [5 empty] | 100
Final Regression | [5 empty] | 60
Beta Feedback & Bug fixes |  |  |  | 50 | 60 | 50 | 5
ThreatVue | 90
Improved list configuration |  | 4 | 6 | 0 | 8 | 5 | 1
Introduce concept of "blacklist" |  | 6 | 6 | 6 | 10 | 6 | 2
List import/export |  | 5 | 6 | 6 | 6 | 6 | 1
Upgrade | 180
Upgrade: NGS 3.0 - SV 3.6.6 |  |  | 10 | 25 | 25 | 55 | 5
Upgrade: SV 3.6.0/3.6.5 - 3.6.6 |  |  | 5 | 5 | 5 | 40 | 5
| 2523.7 | 135 | 133 | 575.5 | 647.5 | 859 | 113.7

## Tasks & Estimates (hidden)
|  | Development | [5 empty] | QA |  |  | Doc
|  | Design |  |  | Code(Person Hours) |  |  | Test Case(Person Hours) |  |  |  |  | July Avail/head(23 days * 8 hours) | 184
Task | Sub Task | Identification | Document | Review | Changes | Testing | Review | Analysis | Development | Execution |  | Total |  | Person Hours | Leaves | Comments
July-Sprint | [12 empty] | Development - 19
Merge NGS v3.0 features in SecureVue | [10 empty] | 16 | 16 | Ashok Kumar Dheekollu | 144 | 5
| Activation |  |  |  | 14 | 8 | 2 |  | 8 | 8 |  | 40 | Hemanth Abbina | 168 | 2
| Unified Node License |  |  |  | 80 | 56 | 8 |  | 32 | 48 |  | 224 | Kullayappa Macha | 184 | 0
| Node Management/Removal of Bulk License |  |  |  | 40 | 32 | 16 | 4 | 36 | 120 |  | 248 | Lavanya Kumar Pulikollu | 147.2 | 0 | Func.Man
Feature Driven Framework | [11 empty] | 0 | Mallikarjun Baddur | 184 | 0
Manage-External-Interfaces: Node Management | [7 empty] | 8 | 40 | 80 |  | 128 | Prakash Reddy Dwarampudi | 184 | 0
| Backend: Restricting 'Manage Node' to Products of Cfg-Subsystem (Add, Edit, Load) |  |  |  | 32 | 12 | 5 |  |  |  |  | 49 | Ramakrishna Panguluri | 88 | 1 | Scrum.Mas
| Backend: Managing Node as Free/Premium |  |  |  | 32 | 12 | 5 |  |  |  |  | 49 | Ramu Mallela | 184 | 0
| Backend: Converting Free Nodes to Premium, Licensed/Managed Node to Premium when upgrade from earlier versions |  |  |  | 32 | 12 | 6 |  |  |  |  | 50 | Ravikiran Aita | 168 | 2
| GUI: Support for Free or Premium Node Type, Allow to manage only supported products |  |  |  | 40 | 8 | 4 |  |  |  |  | 52 | Ravikumar Vallabhu | 184 | 0
| GUI: Node Association by Node Type (free/premium), Node Association by supported product |  |  |  | 32 | 8 | 4 |  |  |  |  | 44 | Santhosh Kumar Varala | 147.2 | 0 | ARB
| GUI: Right-click actions on Data Collector/Device/Host/Group |  |  |  | 56 | 8 | 4 |  |  |  |  | 68 | Santosh Kumar Mantripragada | 184 | 0
| GUI: Edit Host Changes, Configure Devices/Hosts changes, Configure Nodes (Assign/Manage Whitelist), Load supported devices/hosts |  |  |  | 48 | 8 | 4 |  |  |  |  | 60 | Sarat Kumar Kotha | 88 | 1 | Also in 3.6.5
Manage-External-Interfaces: Collection Policies | [7 empty] | 4 | 32 | 60 |  | 96 | Sreenivasa Reddy Palle | 168 | 2
| Backend: Restricting Collection Policies to 'Policy-Types options' of Cfg-Subsystem |  |  |  | 32 | 12 | 4 |  |  |  |  | 48 | Sudhir Pavan Nayudu | 134.4 | 2 | Func.Man
| Backend: Restricting Free Nodes to Free Collection Policies, Restricting Premium Nodes to Premium Collection Policies |  |  |  | 40 | 16 | 4 |  |  |  |  | 60 | Suneetha Nunnaboyina | 160 | 3
| Backend: Reset Collection Policy for Free Nodes after converting Free configuration to Premium, Reset Collection Policy after Premium Evaluation configuration Expired |  |  |  | 32 | 12 | 4 |  |  |  |  | 48 | Varma P K Kokkerlapati | 134.4 | 2 | ARB
| Backend: When upgrading from earlier versions limiting Collection Policies to 'options' |  |  |  | 24 | 12 | 4 |  |  |  |  | 40 | Venkateshwarlu Yalamandala | 184 | 0
| GUI: Load Device/Host tabs based on supported products, Load list of collection policies based on supported data types, Load New/Edit Collection Policy settings based on supported data types |  |  |  | 48 | 16 | 5 |  |  |  |  | 69 | Vivek Ananda Mittagunta | 147.2 | 0 | Func.Man
| GUI: Support Collection Policy templates based on supported data types. |  |  |  | 16 | 8 | 3 |  |  |  |  | 27 | QA - 8
Manage-External-Interfaces: Restricting queries to Report 'module options' of Cfg-Subsystem | [7 empty] | 8 | 40 | 96 |  | 144 | Ashok Pallamala | 184 | 0
| Backend: Loading Queries.xml and extdbreports.xml as per 'module options', Loading sourcecols.xml as per 'module options', Loading drillmap.xml as per 'module options' |  |  |  | 56 | 20 | 8 |  |  |  |  | 84 | Madhusudhan Dommaraju | 92 | 0 | Scrum.Mas
| Backend: Streaming enabled queries.xml, sourcecols.xml to UI, Restricting Reports to enaled sources from Profiles, SDK, Dashboards, Discarding Reporting commands if module is not enabled |  |  |  | 24 | 16 | 8 |  |  |  |  | 48 | Mallika Sri Vaddi | 184 | 0
| GUI: Reports - SourceCols Store - Loading of sourcecols container |  |  |  | 24 | 8 | 4 |  |  |  |  | 36 | Pavan Kumar Patimalla | 176 | 1
| GUI: Reports - Changes in Reports main UI - Handling of context menu enable status/Handling of toolbar items enable status/Reporting workbench changes as per module availability |  |  |  | 40 | 8 | 4 |  |  |  |  | 52 | Ravi Sankar Rekam | 184 | 0
| GUI: Reports - Reporting filters - Loading of module specific filters, Reporting filters - Adding of SNMP and WMI template sources, Custom Reports - Adding of SNMP and WMI template sources |  |  |  | 48 | 8 | 4 |  |  |  |  | 60 | Sireesha Rajana | 90 | 0.5 | Scrum.Mas
| GUI: Scheduled Reports - New Report - Module check to show compliance report templates/Module check for "By time reports" option |  |  |  | 24 | 10 | 4 |  |  |  |  | 38 | Uday Phani Kumar More | 168 | 2
| GUI: Scheduled Reports - Toolbar changes as per module availability, Loading of applicable Report templates |  |  |  | 32 | 10 | 4 |  |  |  |  | 46 | Vijay Babu Begari | 184
Manage-External-Interfaces: Restricting Monitors and Alerts modules to 'options' in Cfg-Subsystem | [7 empty] | 8 | 28 | 36 |  | 72 | Documentation - 2
| Backend: Loading monpolicies.xml as per 'module options', Loading monitors.xml as per 'module options' |  |  |  | 48 | 24 | 4 |  |  |  |  | 76 | Satish Chandra Kamma | 73.6 | 0
| Backend: Limiting Static Monitors |  |  |  | 24 | 12 | 4 |  |  |  |  | 40 | Pratap Dirisala | 184 | 0
| GUI: Changes in Manage Monitors based on enabled monitor types & modules |  |  |  | 24 | 12 | 4 |  |  |  |  | 40 | Total Available Person Hours | 4502 | 23.5
| GUI: Loading filters and output columns in EventViewer, Loading the applicable actions in Workbench |  |  |  | 16 | 12 | 4 |  |  |  |  | 32 | Total Required Person Hours | 4504
Manage-External-Interfaces: Restricting Forensics Search types to 'options' in Cfg-Subsystem | [7 empty] | 8 | 32 | 40 |  | 80 | Gap | -2
| Backend: Limiting Search requests to enabled data sources |  |  |  | 20 | 8 | 4 |  |  |  |  | 32
| GUI: Loading Data Sources for Forensic Search, Loading Node Filter UI for Forensic Search, Import Saved Searched based on enabled data sources |  |  |  | 40 | 24 | 8 |  |  |  |  | 72
Manage-Store: Removing License Node checks as already restricting through 'Manage Node' | Forensics, ParserEngine, Monitoring |  |  |  | 48 | 16 | 8 | 4 | 12 | 12 |  | 100
Manage-Cache: Use GUI Config Info Cache to enable supported modules & menus in UI Navigation | GUI: Filtering of Main modules, Update Config Resources class with Config System details |  |  |  | 40 | 16 | 8 | 4 | 16 | 24 |  | 108
Manage-Cache: Use GUI Config Info Cache to load only enabled components in the NodeVue UI | GUI: Unification of components or monitors, Loading of node summary panel details based upon the applicability, Loading of Config, Asset and Vuln summary details |  |  |  | 32 | 8 | 8 | 8 | 20 | 32 |  | 108
Manage-Cache: Use GUI Config Info Cache to list enabled modules in User Manager UI | GUI: Load modules in New User Role depending on the enabled modules |  |  |  | 16 | 8 | 8 | 8 | 24 | 24 |  | 88
Design: Ability to alert/report/forensics on ThreatVue Control Status |  |  | 72 | 24 | [7 empty] | 96
Design: Improved list configuration |  |  | 32 | 16 | [7 empty] | 48
Design: Table of Contents for Alerts |  |  | 72 | 24 | [7 empty] | 96
Design: Introduce concept of "blacklist" |  |  | 32 | 16 | [7 empty] | 48
Design: List import/export |  |  | 32 | 16 | [7 empty] | 48
Design - Rework: R&A Configuration Subsystem |  |  | 32 | 16 | [7 empty] | 48
Design - Rework: R&A SV 3.6.6 Configurations |  |  | 32 | 16 | [7 empty] | 48
Doc: 366 documentation groundwork | [10 empty] | 186 | 186
Bug Verification QA (10 tasks * 1.5 days + 2 tasks *0.5 days) | [11 empty] | 128
Bug Filing QA (10 tasks * 1.5 days + 2 task *0.5 days) | [11 empty] | 128
Administrative Tasks (*1.5 days/person) | [11 empty] | 348
Miscellaneous Tasks (*2 days/person+ARB...) | [11 empty] | 510
|  | 0 | 304 | 128 | 1154 | 460 | 178 | 64 | 320 | 580 | 202 | 4504
August-Sprint <Yet to work>
Merge NGS v3.0 features in SecureVue | [10 empty] | 10 | 10
| Installation |  |  |  | 120 | 16 | 16
| License Upgrade |  | 80 | 40 | 104 | 24 | 8
| Node Discovery |  |  |  | 40 | 24 | 8
| ThreatVue |  |  |  | 104 | 48 | 16
| Node IPs across multiple DCs of same network |  |  |  | 88 | 24 | 16
| Misc - Data Collection/ Aggregation interval/Delta rotation interval |  |  |  | 8 | 4 | 4
Feature Driven Framework
Alert supporting evidence (Subject Line) |  |  |  |  | 12 | 8 | 4 |  | 8 | 16 | 4 | 52
Ability to alert/report/forensics on ThreatVue Control Status |  |  | 80 | 40 | [6 empty] | 16 | 136
| Alert |  |  |  | 40 | 20 | 8 |  | 20 | 24 |  | 112
| ELF construcyion on Delta & Monitoring |  |  |  | 20 | 16 | 4 | 6 |  |  |  | 46
| Parsing |  |  |  | 12 | 16 | 4 | 6 |  |  |  | 38
| Reporting |  |  |  | 64 | 20 | 8 |  | 24 | 32 |  | 148
| Forensics |  |  |  | 28 | 20 | 4 |  | 24 | 24 |  | 100
12.1 - No unauthorized administrator accounts | [10 empty] | 8 | 8
| Data Collection - Users |  |  |  | 8 | 8 | 4 | 4 |  |  |  | 24
| Whitelist - Users |  |  |  | 40 | 8 | 8 | 4 | 16 | 24 |  | 100
| Control Evaluation |  |  |  | 12 | 8 | 4 | 4 | 16 | 24 |  | 68
12.3 - Require changing passwords | [10 empty] | 8 | 8
| Data Collection |  |  |  | 8 | 8 | 4 | 4 |  |  |  | 24
| Control Evaluation |  |  |  | 20 | 8 | 4 | 4 | 20 | 32 |  | 88
12.5 - Require complex passwords | [10 empty] | 8 | 8
| Data Collection |  |  |  | 8 | 8 | 4 | 4 |  |  |  | 24
| Control Evaluation |  |  |  | 20 | 8 | 4 | 4 | 20 | 32 |  | 88
12.9 - Restrict password reuse | [10 empty] | 8 | 8
| Data Collection |  |  |  | 8 | 8 | 4 | 4 |  |  |  | 24
| Control Evaluation |  |  |  | 20 | 8 | 4 | 4 | 20 | 32 |  | 88
Refresh OpenSSL | [7 empty] | 8 | 8 | 56 |  | 72
| Build Win32/64 |  |  |  | 16 | 8 | 4 |  |  |  |  | 28
| Build Linux32/64 |  |  |  | 16 | 8 | 4 |  |  |  |  | 28
| Compilation & Linking |  |  |  | 24 | 8 | 4 |  |  |  |  | 36
Ability to limit concurrent sessions of same username | [8 empty] | 16 | 24 | 8 | 48
| Mainengine |  |  |  | 36 | 16 | 4
| User Settings |  |  |  | 12 | 8 | 4
Link the entire threat path |  |  |  |  | 12 | 1 | 4 |  | 12 | 12 | 8 | 49
Remove tree at flow reports | [11 empty] | 0
Better status on ThreatVue evaluation | [11 empty] | 0
Improved list configuration | [11 empty] | 0
Table of Contents for Alerts | [11 empty] | 0
Port/protocol sub-control (flows) | [11 empty] | 0
Port/protocol sub-control (firewall allow) | [11 empty] | 0
SANS20 Control Mapping | [11 empty] | 0
Introduce concept of "blacklist" | [11 empty] | 0
List import/export | [11 empty] | 0
Remove license checks post collection (parsing, etc.,)
Defects\enhancements in BZ pushed from 3.0 | [11 empty] | 0
Evaluate SANS Gaps | [11 empty] | 0
Merge from Q1H2 content release
Upgrade: SV 3.6.0/SV 3.6.5/NGS 3.0 - 3.6.6 (License…..) | [11 empty] | 0
October-Sprint
Scalability Setup
Bugs already targeted to SV 3.6.6
UI Bug Fixes
Backend Bug Fixes
UI: Miscellaneous Tasks
Backend: Miscellaneous Tasks
Docs: Miscellaneous Tasks
QA: Miscellaneous Tasks
QA: Bugs Filing and Verification
Administrative Tasks
QA: Patches & September-Sprint Bug Verification
Sanity and Regression Testing
Upgrade Testing | SV 3.6.0 -> SV 3.6.6, SV 3.6.5 -> SV 3.6.6, NGS 3.0 -> SV 3.6.6
Final Regression
Deployment Guide
User Guide
Getting Start Guide
Review Release Notes
Grand Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on I3: Madhusudhan D: Settings+Test Data Feed
Note on J3: Madhusudhan D: Includes review also
Note on A134: Madhusudhan: License check removal was being implemented as part of Product Configurability
Note on A155: Madhusudhan: Each task is assigned 8hrs for Bug Filing & 8hrs for Bug Verification
Note on A157: Madhusudhan: May-Sprint bugs yet to fix

## Plan
[6.11.7] Patch Release Milestones
| Sr. No. | Milestone | Planned Date | Revised Target Date | Actual Date | Remarks
| 1 | Appreciation/Feasibility Analysis Completed | 2020-11-04 |  | 11/03/2020 | Reach out to Joe Lopez and Louis Lodel in Engineering Support for a list of escalations.
| 2 | Release Content Finalized | 2020-11-04 |  | 11/03/2020
| 3 | Design Completed | 2020-11-04 |  | 11/03/2020
| 4 | Design Review/Approval | 2020-11-04 |  | 11/03/2020
| 5 | Obtain IT approval for release date | 2020-11-05 |  | 11/03/2020 | Target date for when the patch plan is completed. Complete request for any prod., UAT and demo deploys related to project: https://corpus.abilitynetwork.com/IT/_layouts/15/start.aspx#/
| 6 | Development Completed | 2020-11-20 |  | 11/30/2020
| 7 | Test Cases Prepared | 2020-11-20 |  | 11/30/2020
| 8 | Build Ready | 2020-11-20 |  | 11/30/2020
| 9 | Build deployed on Test Environment | 2020-11-20 |  | 11/30/2020
| 10 | Deployment Instructions sent to DevOps | 2020-11-26 |  | 11/02/2020 | Gives DevOps time to create chef recipes.
| 11 | QA Testing Completed | 2020-11-27 |  | 11/30/2020
|  | Bug Fixes | 2020-11-30 |  | 12/02/2020
|  | QA Testing Completed 2 | 2020-12-01 |  | 12/02/2020
| 12 | UAT/Adjunct Deployment (optional) | N/A
| 13 | UAT/Adjunct Testing Completed (optional) | N/A
| 14 | Load Testing (optional) | 2020-12-04 |  | 2020-12-07 | When done Inform Devops they can deploy to DEPL. Had to rebuild machine. https://corpus.abilitynetwork.com/engineering/Product Programs/All Payer Claims/Releases/6.11.7/Load test Comparison Report between 6.11.6 and 6.11.7 runs.xlsx
| 15 | Upgrade/Migration Testing | 2020-12-07 |  | 2020-12-07
| 16 | Regression Testing Completed | 2020-12-08 |  | 2020-12-08 | RG-12/08: Regression Testing Completed
| 17 | Engineering Release Review Meeting | 2020-12-08 | 2020-12-09
| 18 | Send Deployment Approval Request | 2020-12-09
| 19 | QA Test Chef Deployment on DEPL | 2020-12-09 | 2020-12-15 |  | After Devops runs chef recipes the code for this release will be on DEPL.
| 20 | Production Deployment | 12/16/2020 |  |  | For scheduled patches, this should take place 5 business days AFTER Deployment Approval Request Update deployment info on the 2020 Projects Sheet: https://corpus.abilitynetwork.com/engineering/Product%20Programs/2020%20Q1-Q4%20Projects.xlsx
| 21 | Rebase Main | 2020-12-17
Release Theme: Security (Pen Test), dropping tls1.0 and tls1.1 and general improvements
Description: Monthly Release
Impact: customer escalations, more secure website and general improvements

## Candidate List
Tech Scoping Doc ID | Title/Desc | TFS / JIRA ID | Developer | QA | TC# | Reg TC | Feature Status | Dev % | QA Plan % | QA Exec % | Initial T-Shirt Size | Total Effort in Person Days from Scoping Document | Product Investment Mix Category | Type of Work Category | Business Justification | Comments/Notes | Design Review Comments | QA Testing Strategy | UAT Strategy
1.1 | APC - Pen Test : Frameable response (clickjacking) | 235043 | Haritha | NA |  |  | Done | NA | NA | NA | S | 2 | OpEx - Not Customer | OpEx - Not Customer | NA | Testing covered in regression tests
1.2 | APC - Pen Test : Browser cross-site scripting filter misconfiguration | 235044 | Rajeev | NA |  |  | Done | NA | NA | NA | S | 2 | OpEx - Not Customer | OpEx - Not Customer | NA | Testing covered in regression tests
1.3 | APC - Pen Test : Content sniffing not disabled | 235045 | Bhasker | NA |  |  | Done | NA | NA | NA | S | 2 | OpEx - Not Customer | OpEx - Not Customer | NA | Testing covered in regression tests
1.5 | Duplicate Session (35732296) created | 235291 | Bhasker | Ravi | 1 |  | Done | 100% | 100% | 100% | L | 12 | Customer Escalations | Customer Escalations | Customer Retention
1.7 | Date (<01/01/1900) validation for Patient Statements, Session Results, Rejection Center, Payer Claim/Statistics & Transmission Report pages | 219167 | Greg\Bhasker | Pavan | 3 |  | Done | 100% | 100% | 100% | M | 8 | OpEx - Not Customer | OpEx - Not Customer | NA
1.8 | Welink, LinkUB, ClaimEditor: In case we try injecting XSS sensitive information in the application URL, we see a Runtime Error (yellow page) | 228672 | Rajeev | Ravi | 2 | 2 | Done | 100% | 100% | 100% | L | 12 | Tech/Platform | OpEx - Not Customer | NA
1.12 | Improve Reject Messages - Generals (Backend Setup) | 240735 | Jahnavi | Ritu Gupta | 1 |  | Done | 100% | 100% | 100% | L | 12 | Market Enhancement | New Feature - Construction | NA
Items Added after Initial Candidate List (escalations, etc.)
1.9 | LINKUB - Edit for admission date before date of service. | 238634 | Bhasker | Ritu Gupta | 2 |  | Done | 100% | 100% | 100% | S | 4 | Customer Escalations | Customer Escalations | Customer Retention
1.11 | Drop tls1.0 and tls1.1 | 240202 | James | QA |  |  | Done | 100% | 100% | 100% | S | 4 | Tech/Platform | OpEx - Not Customer | Regulatory
9
Non-Standard Deploys
Internal Items (To be worked on if time is available)
Items Removed from Initial Candidate List
1.4 | AMA Reporting for NPI's using CPT Logic | 236991 | Haritha | Ritu Gupta |  |  | Research |  |  |  | L | 12 | Market Enhancement | New Feature - Construction | NA | Did not get requirements document in time for this release.
1.6 | Improve Reject Messages - Generals | 223087 | Jahnavi | Ritu Gupta |  |  | Done | 100% | 100% | 100% | L | 12 | Market Enhancement | New Feature - Construction | NA | Replaced with 240735
T-Shirt Size Key
XS | 1 day or less
S | 2-4 days
M | 5-8 days | [18 empty] | Investment Mix | [5 empty] | Business Justification
L | 9-14 days | [18 empty] | 0% | New Saleable Features or Product |  |  |  |  | 24.24% | Customer Retention
XL | 15-19 days | [18 empty] | 19.51% | Tech/Platform |  |  |  |  | 0% | Bookings
XXL | 20+ days | [18 empty] | 17.07% | Sustaining & Cust Ops |  |  |  |  | 0% | Operational
[20 empty] | 43.9% | Market Enhancement |  |  |  |  | 6.061% | Regulatory
[26 empty] | 93.94% | NA
[19 empty] | INV MIX |  |  |  |  | Business Justification
[20 empty] | # Days | %
[19 empty] | Customer Escalations | 16 | 19.51% |  |  |  | # Days | %
[19 empty] | Market Enhancement | 36 | 43.9% |  |  | Customer Retention | 16 | 24.24%
[19 empty] | Tech/Platform | 16 | 19.51% |  |  | Bookings | 0 | 0%
[19 empty] | OpEx - Customer Operations | 0 | 0% |  |  | Operational | 0 | 0%
[19 empty] | OpEx - Not Customer | 14 | 17.07% |  |  | Regulatory | 4 | 6.061%
[19 empty] | New Saleable Features or Product | 0 | 0% |  |  | NA | 62 | 93.94%
[19 empty] | Total | 82 |  |  |  | Total | 66
Type of Work
[22 empty] | 34.78% | Customer Escalations
[22 empty] | 0% | New Feature
[22 empty] | 0% | OpEx - Customer Support
[22 empty] | 65.22% | OpEx - Not Customer
Type of Work
[20 empty] | # Days | %
[19 empty] | Customer Escalations | 16 | 34.78%
[19 empty] | New Feature | 0 | 0%
[19 empty] | OpEx - Customer Support | 0 | 0%
[19 empty] | OpEx - Not Customer | 30 | 65.22%
[19 empty] | Total | 46
Note on L1: Sandra Speikers: See t-shirt sizes key below for reference
Note on N1: Sandra Speikers: See "List&Definitions" tab for Investment Mix definitions.
Note on O1: Sandra Speikers: Customer Esc -> Customer Esc New Feature or Tech/Platform -> New Feature OPEX-> OPEX
Note on P1: Cindy Lee: Work with Product Management to define

## IT Dependencies
Infrastructure and Hardware Needs
Item | Environment | Requirements | Due Date | Date Service Desk Ticket Created | Who created Ticket | Ticket # | Date Completed | Notes

## Source Control
[6.11.7]
merge after prod deploy
Sequence Number | Action Date | Source Management Action Description | Branch Fully Qualified URL / Path
1 | 2020-11-04 | Created the 6.11.7 branch from 6.11.6 branch
2 | 2020-11-23 | Merged 6.11.6 into master and master into 6.11.7
3
5
6
7
8
9
10
11

## Issues
# | Date Opened | Requirement | Issue | Status | Comments | Estimated Days Impacted | Helpdesk Ticket
Note on E1: Status Values: 1.) Open 2.) Work 3.) Closed 4.) Canceled 5.) Deferred

## Defect Status
Week (Ending Saturday) | New Opened | Done/Fixed | Total Open | # Critical in Open state | # High in Open state | Misc | Comments
Browser Support
Browser | New TC's Created | Regression Tests | Total TC's Planned | Total TC Executed | Pass | Supported | Notes
IE 7
IE 8
IE 9
IE 10
IE 11
Edge
Chrome
Firefox
Total | 0 | 0 | 0 | 0 | 0
Regression Cycle
Functional Area | New TC's Created | Regression Tests | Total TC's Planned | Total TC Executed | Pass | Automated # | Fail | No Run | new defects | old defects | Comments
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Traceability
Traceability Matrix
ID | Escalation | TFS Id | Design | Design Review | Design Approval | Code | Code Review | DBA Review | Unit Test(s) | Test Case Review | Test Case Execution | UAT | BugFix/ Performance Tests | Comments
1.1 | APC - Pen Test : Frameable response (clickjacking) | 235043 | NA | NA | NA | Yes | Yes (James, Bhasker, Rajeev and Jahnavi) | NA | NA | NA | NA | NA | NA
1.2 | APC - Pen Test : Browser cross-site scripting filter misconfiguration | 235044 | NA | NA | NA | Yes | Yes (James, Bhasker, and Jahnavi) | NA | NA | NA | NA | NA | NA
1.3 | APC - Pen Test : Content sniffing not disabled | 235045 | NA | NA | NA | Yes | Yes (James and Jahnavi) | NA | NA | NA | NA | NA | NA
1.5 | Duplicate Session (35732296) created | 235291 | NA | NA | NA | Yes | Yes (Jahnavi, James and Rajeev) | NA |  | Yes | Yes | NA | NA
1.7 | Date (<01/01/1900) validation for Patient Statements, Session Results, Rejection Center, Payer Claim/Statistics & Transmission Report pages | 219167 | NA | NA | NA | Yes | Yes (Bhasker, Rajeev, Jahnavi and James) | NA |  | Yes | Yes | NA | Yes
1.8 | Welink, LinkUB, ClaimEditor: In case we try injecting XSS sensitive information in the application URL, we see a Runtime Error (yellow page) | 228672 | NA | NA | NA | Yes | Yes (Jahnavi and James) | NA |  | Yes | Yes | NA | Yes
1.12 | Improve Reject Messages - Generals (Backend Setup) | 240735 | Yes | Yes | Yes | Yes | Yes (James) | Yes |  | Yes | Yes | NA | Yes
1.9 | LINKUB - Edit for admission date before date of service. | 238634 | NA | NA | NA | Yes | Yes (James and Jahnavi) | Yes |  | Yes | Yes | NA | NA
1.11 | Drop tls1.0 and tls1.1 | 240202 | NA | NA | NA | Yes | Yes (Rajeev and Jahnavi) | NA | NA | NA | Yes | NA | Yes
Risk/Mitigation (if applicable)
1
2
.
Limited Release Status Update (if applicable)
Note on D3: Jake Gentry: N/A means effort not significant enough to warrant separate document. Design included in scoping document if at all.
Note on E3: Jake Gentry: N/A automatically if Design is N/A
Note on J3: Jake Gentry: N means no new unit tests were created. Y means new tests created.

## Resources
Dev & QA Resources
Engineer | Total Available Working Days | November
Working Days in month | 13 | 13
James Blythe | 0 | 5.75
Greg Checovetes | 0 | 7.7
Jahnavi Gandhavalla | 0 | 2.5
Bhasker Bandi | 0 | 10.7
Haritha Madireddy | 0 | 7.7
Rajeev Kumar | 0 | 11.7
Ravi Kumar Giddalur | 0 | 11.7
Ritu Gupta | 0 | 4.7
Pavan Patimalla | 0 | 11.7
Total Eng Days | 0 | 46.05
Assumptions:
50% utilization for Tech Lead
50%utilization for QA
90% utilization for team
Estimated PTO:
James Blythe | November | 4
Greg Checovetes | November | 4
Jahnavi Gandhavalla | November | 0
Bhasker Bandi | November | 1
Haritha Madireddy | November | 4
Rajeev Kumar | November | 0
Ravi Kumar Giddalur | November | 0
Ritu Gupta | November | 7
Pavan Patimalla | November | 0
Note on B2: Cindy Lee: Available working days based on target GA date; includes QA testing days

## Retrospective
What went right/ worked well: | What went wrong/Not worked well:
Lessons Learned from previous release to improve on for this release: | Possible Solutions and Action Items
|  | Task | Owner | Date

## Lists&Definitions
Feature Status | Definition |  | Priority
Possible | Being considered |  | 1 - Critical
Research | Researching the item |  | 2 - High
Approved | Approved/Committed (item is in progress) |  | 3 - Med
Analysis Done | Analysis of the item is complete |  | 4 - Low
Scoping Done | Scoping document entry done
Dev Started | Development has begun
Dev Done | Development completed and item needs to be QA tested
QA Started | QA has begun
QA Done | QA is complete
Done | Item has been QA tested. Lead should confirm all associated tasks closed in TFS/JIRA w/ appropriate CAP allocations
Blocked | Blocked (at risk or de-scoped/scope reduced)
Moved to next release | Moved to the next release
Cancelled | Item has been cancelled
Hold | Put on hold
Product Investment Mix Category | Definition
Customer Escalations | Customer and Customer Support originated escalations that fix a defect and/or improve a “working as designed” feature (NOT internally found defects/defects found in the course of QA)
Market Enhancement | New features or enhancements to existing features on current services/products that improve competitiveness of the product / lead to revenue generation. Support new markets (add customer),Regulatory enhancements,Performance/scaling enhancements (including internal tools)
Tech/Platform | Updates to keep technology current or improve; also tools for more efficient administration, deployment and monitoring of systems (e.g. Upgrading an OS, Splunk, etc.). If the work involves coding in the existing product, then it is " Market Enhancements "
OpEx - Customer Operations | Operational work that is being done for Customer Support, including Customer migrations and Implementations support
OpEx - Not Customer | Operational work that is not development (e.g. Helping other teams, PTO, etc.)
New Saleable Features or Product | Net new functionality (feature or product) that can be sold resulting in incremental revenue/new skus. Includes any new products that are less than 2 years old.
Type of Work
Customer Escalations | Only customer escalations NOT internally found defects or defects found in the course of QA
New Feature | New features or advancing existing features on current services/products; includes regulatory enhancements. | Support new markets, Support larger customers, Drive new revenue
OpEx - Customer Support | Operational work that is not development (e.g. EASE migration) | Improvements made to retain existing customers, Customer-specific enhancements/configurations that are non-saleable, regulatory emhanchments
OpEx - Not Customer | PTO, misc. non-project-related work | Indirect
Business Justification | to align with Product roadmaps | Examples
Customer Retention | Retain customers | customer escalations, improving ease of use
Bookings | Support bookings/new revenue | feature enhancements, efficiencies that make product more saleable or increase revenue
Operational | Operational support | Operational efficiency (e.g. makes implementing or billing customers easier)
Regulatory | Regulatory | change driven by regulators such as PDPM, claim attachments, HICN>MBI
NA | Does not fall into one of above categories (e.g. Tech Debt) | none of the above (tech debt such as password, server, framework, browser support